## Definitions
Criterion | Definition | Notes & Purpose
Criticality (VED) | Classification of system dependency level: • V = Vital (critical to operations) • E = Essential (important functions) • D = Desirable (nice-to-have) | Protects system stability and availability. Vital items get higher priority. Focuses on preventing system outages and maintaining core functionality. Maps directly to SLA requirements and customer impact.
Urgency | Time sensitivity of the decision or issue. How quickly action is needed based on: • Immediate business deadlines • Time-dependent opportunities • Expiring constraints | Respects time pressure from market, customers, or internal commitments. Prevents over-analysis of time-sensitive decisions. Balances long-term planning with tactical needs. High urgency doesn't override criticality—consider both together.
Effort | Resources required to implement the decision: • Time commitment • Cost (financial, personnel) • Technical complexity • Disruption risk | Ensures efficient resource allocation. High-effort items need stronger business cases. Prevents overengineering low-impact solutions. Considers opportunity cost of resources. Helps identify quick wins vs. strategic investments.
Business Impact | Expected outcomes and value delivery: • Revenue generation/protection • Cost savings • Customer satisfaction • Risk mitigation • Strategic alignment | Aligns with stakeholder priorities and organizational goals. Quantifiable when possible (revenue, cost, time savings). Qualitative measures acceptable for intangibles (morale, brand, learning). Highest impact items warrant high effort.

## Combined Framework
ENGINEERING DECISION FRAMEWORK
I. ASSESSMENT PHASE
A | Criticality Assessment | Classify component/issue as Vital (V), Essential (E), or Desirable (D) • V = System down, customers impacted • E = Partial functionality lost • D = Feature/improvement, no service loss
B | Urgency Assessment | Determine timeline: • IMMEDIATE (< 24 hours) • SHORT-TERM (1-7 days) • PLANNED (> 1 week) • STRATEGIC (no firm deadline)
C | Effort Estimation | Calculate resource investment: • QUICK: < 4 hours • MODERATE: 4 hours - 3 days • SIGNIFICANT: 3 days - 2 weeks • MAJOR: > 2 weeks
D | Impact Analysis | Quantify business value: • PRIMARY IMPACT (revenue, cost savings, risk) • SECONDARY IMPACT (efficiency, experience) • STRATEGIC ALIGNMENT (roadmap fit)
II. PRIORITIZATION MATRIX
Matrix 1: Criticality vs. Business Impact
Matrix 2: Urgency vs. Effort
III. BALANCED DECISION RULES
Rule 1 | Criticality First | Vital items move forward unless effort is extreme. Even low-impact vital fixes should be scheduled.
Rule 2 | High Impact Justifies High Effort | Strategic investments with large business impact warrant significant resource commitment, even if not immediately urgent.
Rule 3 | Urgency + Low Effort = Priority | Quick fixes that solve urgent problems should be prioritized to maintain momentum and customer trust.
Rule 4 | Resource Constraints Matter | If team capacity is limited, choose fewer high-impact items over many low-impact ones.
Rule 5 | Check Alignment | Verify decisions align with business strategy and team priorities. Outlier items need justification.
IV. DECISION OUTPUT
Status | Priority Level | Mapped decision: • P1 (Critical): Vital + any urgency + justified effort • P2 (High): Essential + high impact OR urgent + low effort • P3 (Medium): Non-critical + moderate impact • P4 (Low): Desirable + low impact + low urgency

## Quick Reference
DECISION FRAMEWORK SUMMARY
Purpose | Balanced framework for engineering decisions that considers system stability, time constraints, resources, and business value
Best For | Prioritizing technical work, allocating engineering resources, balancing multiple competing initiatives
Key Principle | No single factor dominates. All four dimensions must be evaluated together for sound decisions.
Who Uses It | Engineering teams, tech leads, product managers, stakeholders
When To Use | Sprint planning, incident response, roadmap prioritization, resource allocation decisions
Critical Success Factor | Honest assessment of all dimensions. Avoid bias toward one factor.
Common Mistake | Letting urgency override business impact, or ignoring feasibility in effort estimation
Expected Outcome | Transparent, defensible decisions that balance stability, speed, efficiency, and value